## Read Me
The Data Migration Toolkit
TEMPLATE
What this is | The working sheets for running a data migration end to end, one tab per artefact, in the order you need them.
The eight stages | Kickoff and scope. Profile the source. Map the fields. Clean and de-dupe. The dry run. User acceptance testing. Freeze, cutover and bridge. Hypercare and close. Every stage ends at a gate, and a gate is a stage you do not leave until somebody signs.
THE TABS
Overview | Progress by stage, calculated from the plan.
Migration Plan | The task list. Set Status and % Complete as you go.
Action Log | Every action and decision, with an owner and a date. Your chase list.
Change Requests | Anything asked for that was not in the signed scope. Log it the same day.
Field Mapping | Source field, target field, the rule, and who signed it off.
Exception Sheet | What the cleaning rules could not fix. The client decides each one.
Reconciliation | Counts and control totals, source against target. Run before and after.
Linkage Check | Every document ties to a record. Anything that does not is an orphan.
Gate Sign-off | One row per gate, who signed and when. This is your evidence.
IMPORTING TO SMARTSHEET
What imports cleanly | Migration Plan, Action Log, Change Requests, Field Mapping, Exception Sheet and Gate Sign-off are built for it: header on row 1, no merged cells, no formulas, real dates.
What does not | Overview, Reconciliation and Linkage Check use formulas. Smartsheet cannot import a cross-sheet formula. Import those only if you intend to rebuild the formulas as Smartsheet column formulas. They work as they are in Excel.
How to import | File, then Import, then Microsoft Excel. Tick "first row is a header". Smartsheet takes one sheet per file, so save the tab you want as its own workbook first.
Predecessors | The Predecessors column holds row numbers, which is what Smartsheet expects. Switch on Dependencies in Project Settings after import and it wires the chain up for you.
Hierarchy | Excel cannot carry indentation across. After import, select the tasks under each stage row and indent them once to rebuild the parent and child structure.
Column types | After import: Status to a dropdown (Not Started, In Progress, Done, Blocked, N/A), % Complete to a percentage, Owner to a contact column, Start and Finish to dates.
FILLING IT IN
Blue text | Every cell in blue is an example showing the format expected. Delete the example row once you have your own data.
Owners are roles | Owners are roles rather than names on purpose. Replace them with your own people.
Dates are blank | Set your own kickoff on the Overview tab, then work the durations out from there. Durations in the plan are a starting point, not a promise.
The Data Migration Toolkit — Michael Nocito

## Overview
Data Migration — Live Tracker
Client | Your client
Moving from | Legacy system
Moving to | Target system
Scope | What is in scope
Migration lead | Migration Lead
Kickoff
Target go-live
Progress by stage
Stage | % Done
Stage 1 — Kickoff and Scope
Stage 2 — Profile the Source
Stage 3 — Map the Fields
Stage 4 — Clean and De-dupe
Stage 5 — The Dry Run
Stage 6 — User Acceptance Testing
Stage 7 — Freeze, Cutover, Bridge
Stage 8 — Hypercare and Close
Document Digitization (parallel)
Backfile (T plus 6 months)
OVERALL
This tab uses cross-sheet formulas, so it will not import to Smartsheet. See the Read Me.

## Migration Plan
# | Task ID | Task Name | Stage | Owner | Status | % Complete | Start | Finish | Duration (days) | Predecessors | Deliverable / Gate | Guide | Notes
| 1 | Stage 1 — Kickoff and Scope
1 | 1.1 | Internal handoff from Sales | Stage 1 — Kickoff and Scope | Sales / Account | Not Started | 0% |  |  | 2 |  | Scope, promises and stakeholders reviewed before the client sees you | migration-kickoff-scope
2 | 1.2 | Client kickoff meeting | Stage 1 — Kickoff and Scope | Migration Lead | Not Started | 0% |  |  | 1 | 1 | Agenda run in order; everyone knows who does what | migration-kickoff-scope
3 | 1.3 | Ask the four questions | Stage 1 — Kickoff and Scope | Migration Lead | Not Started | 0% |  |  | 2 | 2 | Success defined, contract signer known, data decision maker named, recovery plan agreed | migration-questions
4 | 1.4 | Agree a single point of contact | Stage 1 — Kickoff and Scope | Client PM | Not Started | 0% |  |  | 1 | 3 | One name, not an address book | migration-kickoff-scope
5 | 1.5 | Write the exclusion list | Stage 1 — Kickoff and Scope | Migration Lead | Not Started | 0% |  |  | 3 | 4 | What is NOT moving, in writing | migration-kickoff-scope
6 | 1.6 | Confirm source systems and access | Stage 1 — Kickoff and Scope | Client IT | Not Started | 0% |  |  | 3 | 5 | Read access granted, export method proven | migration-kickoff-scope
7 | 1.7 | Agree what happens to work created during the migration | Stage 1 — Kickoff and Scope | Client PM | Not Started | 0% |  |  | 1 | 6 | The gap is named before it opens | migration-cutover
8 | 1.8 | GATE — scope signed off | Stage 1 — Kickoff and Scope | Client PM | Not Started | 0% |  |  | 1 | 7 | Signed scope. Nothing else starts until this exists. | migration-kickoff-scope
| 2 | Stage 2 — Profile the Source
9 | 2.1 | Take the full initial export | Stage 2 — Profile the Source | Client IT | Not Started | 0% |  |  | 2 |  | Everything, not a sample | migration-profiling
10 | 2.2 | Run the seven checks | Stage 2 — Profile the Source | Migration Lead | Not Started | 0% |  |  | 5 | 9 | Row counts, blanks, duplicates, formats, ranges, orphans, encoding | migration-profiling
11 | 2.3 | Turn each finding into a decision | Stage 2 — Profile the Source | Migration Lead | Not Started | 0% |  |  | 3 | 10 | A finding with no decision is a finding you will meet again at cutover | migration-profiling
12 | 2.4 | Re-plan where profiling changed the estimate | Stage 2 — Profile the Source | Migration Lead | Not Started | 0% |  |  | 2 | 11 | Revised plan, with the reason attached | migration-scope-creep
13 | 2.5 | GATE — profiling report accepted | Stage 2 — Profile the Source | Client PM | Not Started | 0% |  |  | 1 | 12 | Client has seen the true state of their data | migration-profiling
| 3 | Stage 3 — Map the Fields
14 | 3.1 | Source to target mapping — records | Stage 3 — Map the Fields | Migration Lead | Not Started | 0% |  |  | 8 |  | Every field has a home, a rule and a reason | migration-field-mapping
15 | 3.2 | Document and metadata mapping | Stage 3 — Map the Fields | Migration Lead | Not Started | 0% |  |  | 4 | 14 | Documents are data too | migration-field-mapping
16 | 3.3 | Define the unique ID | Stage 3 — Map the Fields | Migration Lead | Not Started | 0% |  |  | 3 | 15 | One ID ties records and documents together | migration-field-mapping
17 | 3.4 | Decide on fields with nowhere to go | Stage 3 — Map the Fields | Client Data Owner | Not Started | 0% |  |  | 3 | 16 | Each one: move, drop or park, decided by the client | migration-field-mapping
18 | 3.5 | Client review of the map | Stage 3 — Map the Fields | Client PM | Not Started | 0% |  |  | 3 | 17 | Walked through, not emailed and hoped for | migration-field-mapping
19 | 3.6 | GATE — mapping signed off and version frozen | Stage 3 — Map the Fields | Client PM | Not Started | 0% |  |  | 1 | 18 | The signed copy is kept separate from the working copy | migration-file-hygiene
| 4 | Stage 4 — Clean and De-dupe
20 | 4.1 | Write the cleaning rules | Stage 4 — Clean and De-dupe | Migration Lead | Not Started | 0% |  |  | 4 |  | Rules, not one-off edits | migration-cleaning
21 | 4.2 | Preview every rule before applying it | Stage 4 — Clean and De-dupe | Migration Lead | Not Started | 0% |  |  | 3 | 20 | Row counts before and after, every time | migration-cleaning
22 | 4.3 | De-duplicate, deciding which record survives | Stage 4 — Clean and De-dupe | Migration Lead | Not Started | 0% |  |  | 4 | 21 | The client decides the survivor, not the loader | migration-cleaning
23 | 4.4 | Build the exception list | Stage 4 — Clean and De-dupe | Migration Lead | Not Started | 0% |  |  | 3 | 22 | Everything a rule cannot fix | migration-cleaning
24 | 4.5 | Client resolves exceptions | Stage 4 — Clean and De-dupe | Client Data Owner | Not Started | 0% |  |  | 6 | 23 | Decisions logged against each exception | migration-cleaning
25 | 4.6 | GATE — exception list closed or formally accepted | Stage 4 — Clean and De-dupe | Client PM | Not Started | 0% |  |  | 1 | 24 | Open exceptions are a decision, not an oversight | migration-cleaning
| 5 | Stage 5 — The Dry Run
26 | 5.1 | Load everything into the sandbox | Stage 5 — The Dry Run | Migration Lead | Not Started | 0% |  |  | 4 |  | The whole set. A sample proves nothing about volume. | migration-dry-run
27 | 5.2 | Run the six checks | Stage 5 — The Dry Run | Migration Lead | Not Started | 0% |  |  | 4 | 26 | Counts, control totals, links, spot fidelity, processability, integration | migration-dry-run
28 | 5.3 | Log every break and how the loader behaves | Stage 5 — The Dry Run | Migration Lead | Not Started | 0% |  |  | 3 | 27 | The loader log you will still be using next project | migration-dry-run
29 | 5.4 | Fix, reload and re-check | Stage 5 — The Dry Run | Migration Lead | Not Started | 0% |  |  | 5 | 28 | Repeat until the reconciliation is clean | migration-dry-run
30 | 5.5 | GATE — clean reconciliation in sandbox | Stage 5 — The Dry Run | Migration Lead | Not Started | 0% |  |  | 1 | 29 | Issues documented, not just fixed | migration-dry-run
| 6 | Stage 6 — User Acceptance Testing
31 | 6.1 | Choose testers who do the work daily | Stage 6 — User Acceptance Testing | Client PM | Not Started | 0% |  |  | 2 |  | Not managers. People who would notice. | migration-uat
32 | 6.2 | Give testers a script and real scenarios | Stage 6 — User Acceptance Testing | Migration Lead | Not Started | 0% |  |  | 3 | 31 | Ask a question, do not ask for a favour | migration-uat
33 | 6.3 | Run the UAT sessions | Stage 6 — User Acceptance Testing | Client SMEs | Not Started | 0% |  |  | 5 | 32 | Findings captured as they happen | migration-uat
34 | 6.4 | Triage UAT findings | Stage 6 — User Acceptance Testing | Migration Lead | Not Started | 0% |  |  | 3 | 33 | Fix, defer or explain, each one answered | migration-uat
35 | 6.5 | GATE — client signs off UAT | Stage 6 — User Acceptance Testing | Client PM | Not Started | 0% |  |  | 1 | 34 | Written sign-off from the people who tested | migration-uat
| 7 | Stage 7 — Freeze, Cutover and Bridge
36 | 7.1 | Agree and communicate the freeze window | Stage 7 — Freeze, Cutover and Bridge | Client PM | Not Started | 0% |  |  | 2 |  | Everyone knows when the old system stops taking work | migration-cutover
37 | 7.2 | Full cutover rehearsal, timed against the freeze window | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | Not Started | 0% |  |  | 3 | 36 | The whole sequence run end to end, clock running. Proves it fits. | migration-cutover
38 | 7.3 | Take the final delta export | Stage 7 — Freeze, Cutover and Bridge | Client IT | Not Started | 0% |  |  | 1 | 37 | Everything added since the initial export | migration-cutover
39 | 7.4 | Go / no-go decision, with the fallback position named | Stage 7 — Freeze, Cutover and Bridge | Client PM | Not Started | 0% |  |  | 1 | 38 | Who decides, on what evidence, and what happens if it is no | migration-cutover
40 | 7.5 | Cutover, in order | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | Not Started | 0% |  |  | 2 | 39 | Records, then documents, then links | migration-cutover
41 | 7.6 | Bridge import | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | Not Started | 0% |  |  | 2 | 40 | The gap closed, not left for later | migration-cutover
42 | 7.7 | Post-load reconciliation | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | Not Started | 0% |  |  | 2 | 41 | The same six checks as the dry run, on production | migration-cutover
43 | 7.8 | GATE — go-live accepted | Stage 7 — Freeze, Cutover and Bridge | Client PM | Not Started | 0% |  |  | 1 | 42 | Numbers match, client accepts, together | migration-cutover
| 8 | Stage 8 — Hypercare and Close
44 | 8.1 | Agree the hypercare window before you need it | Stage 8 — Hypercare and Close | Client PM | Not Started | 0% |  |  | 1 |  | Length and route agreed in advance | migration-hypercare
45 | 8.2 | Log and resolve what surfaces | Stage 8 — Hypercare and Close | Migration Lead | Not Started | 0% |  |  | 15 | 44 | The long tail, tracked not absorbed | migration-hypercare
46 | 8.3 | Final reconciliation report | Stage 8 — Hypercare and Close | Migration Lead | Not Started | 0% |  |  | 3 | 45 | The proof the move was complete | migration-hypercare
47 | 8.4 | Internal results readout | Stage 8 — Hypercare and Close | Migration Lead | Not Started | 0% |  |  | 1 | 46 | What went well, what to change next time | migration-hypercare
48 | 8.5 | Handoff to Support | Stage 8 — Hypercare and Close | Support / CS | Not Started | 0% |  |  | 2 | 47 | So it lands warmly, with context | migration-hypercare
49 | 8.6 | GATE — project closed, handoff accepted | Stage 8 — Hypercare and Close | Support / CS | Not Started | 0% |  |  | 1 | 48 | Support owns it now, knowingly | migration-hypercare
| DD | Parallel — Document Digitization
50 | DD.1 | Audit paper volume, condition and scope | Parallel — Document Digitization | Client Data Owner | Not Started | 0% |  |  | 5 |  | How much paper, in what state | migration-field-mapping
51 | DD.2 | Select vendor and agree chain of custody | Parallel — Document Digitization | Client PM | Not Started | 0% |  |  | 8 | 50 | Who holds the records, and how it is proven | migration-field-mapping
52 | DD.3 | Define indexing metadata to match the map | Parallel — Document Digitization | Migration Lead | Not Started | 0% |  |  | 4 | 51 | Index to the target fields, not to what is convenient | migration-field-mapping
53 | DD.4 | Scan, OCR, index and QA | Parallel — Document Digitization | Scanning Vendor | Not Started | 0% |  |  | 30 | 52 | Digitized and indexed, ready to link | migration-field-mapping
54 | DD.5 | Day-forward scanning live at go-live | Parallel — Document Digitization | Scanning Vendor | Not Started | 0% |  |  | 1 | 53 | New paper never becomes new backlog | migration-cutover
| BF | Follow-on — Backfile (T plus 6 months)
55 | BF.1 | Backfile scanning continues | Follow-on — Backfile (T plus 6 months) | Scanning Vendor | Not Started | 0% |  |  | 90 |  | The historical paper, on contract | migration-hypercare
56 | BF.2 | Bridge import of historical documents | Follow-on — Backfile (T plus 6 months) | Migration Lead | Not Started | 0% |  |  | 5 | 55 | Loaded and linked by the same unique ID | migration-field-mapping
57 | BF.3 | Reconcile the backfile | Follow-on — Backfile (T plus 6 months) | Migration Lead | Not Started | 0% |  |  | 3 | 56 | Counts tie, no orphans | migration-pitfalls
58 | BF.4 | Decommission paper storage | Follow-on — Backfile (T plus 6 months) | Client PM | Not Started | 0% |  |  | 5 | 57 | The reason the project was funded | migration-hypercare

## Action Log
Action ID | Date raised | Source | Related Task ID | Action or decision needed | Owner | Status | Due | Resolution / notes
A001 | 2026-03-09 | Kickoff meeting | 1.6 | Client to send the legacy systems list and a sample export | Client IT | Open | 2026-03-11
The blue row is an example of the format. Delete it and use your own.

## Change Requests
CR ID | Date raised | Raised by | What is being asked for | In signed scope? | Impact on timeline | Impact on cost | Decision | Decided by | Date decided
CR-01 | 2026-02-26 | Client PM | Add a second legacy system that was not in the export | No | Plus 2 weeks | Plus 1 week effort | Routed to the account owner, not absorbed | Sales / Account | 2026-03-02
The blue row is an example of the format. Delete it and use your own.

## Field Mapping
Source field | Source example | Target field | Transformation rule | Required? | Status | Signed off by | Date signed
client_name | Smith, John | First Name / Last Name | Split on the comma into two fields | Yes | Mapped | Client Data Owner | 2026-05-01
The blue row is an example of the format. Delete it and use your own.

## Exception Sheet
Exception ID | Record ID | Field | Issue | Severity | Client decision | Status | Date resolved
E001 | NW-4471 | Date of Birth | Missing a required value | High | Client to supply from the paper chart | Open
The blue row is an example of the format. Delete it and use your own.

## Reconciliation
Check | Source count | Target count | Difference | Result | When run | Notes
Client records | 0 | 0 |  |  | Dry run | Replace with your own checks
Run the same checks before the load and after it. A difference of zero on every row is the only pass. This tab uses formulas, so it will not import to Smartsheet.

## Linkage Check
Document ID | Document type | Client ID on the document | Found in records? | Result | Client IDs in the target
D-0001 | Consent form | NW-0001 |  |  | NW-0001
Column G is the list of client IDs that exist in the target. An orphaned document is a compliance problem, not a tidy-up job. This tab uses formulas, so it will not import to Smartsheet.

## Gate Sign-off
Gate | Stage | What is being signed | Signed by | Role | Date | Evidence held
G1 | Stage 1 — Kickoff and Scope | The signed scope, including the exclusion list | Name | Client PM | 2026-03-13 | Email, saved to 01-scope
The blue row is an example of the format. Delete it and use your own.